## Projects
Conservation Transactions Department Projections 2016
Project Code | Project Name | Project lead | Acres | Land Type | Role | Close Q | Purchase Price | Comp % | Success Fee | Cost Coverage | Hard Costs | Success Factor (2014) | Discount in Value | Net (not incl staff / other internal costs) | Corridor/Focus Area | Close Q/year | update date | Comments
SN3073 | Whitehorse Mountain | Adam, Susan | 33.6 | Rural | Facilitate purchase for Sno County | [9 empty] | Stillaguamish Watershed | Q1 | 1/22 | Appraisal updated, came in at $290k Landowner recieved two access easements from neighbors that County requires and would raise value. PSA sent to county. CFT contract amended to extend contract date.
SN3074 | Lower Wallace Wetland | Michelle, Susan | 5 | Rural | Facilitate donation of easement | [9 empty] | Great Northern Corridor | Q1 2016 | 1/22 | AD needs to review CE to send to landowner
SN3076 | Faber Farm: Sale | Michelle, Liz, Susan | n/a | Resource | Facilitate purchase of farm on behalf of private farmer Andrew Albert. | [9 empty] | Stillaguamish Watershed | Q1 | 01/14 | Aiming for April closing
SN3081 | Johnson Farm | Michelle, Liz | 160 | Resource | Facilitate purchase of farm for Stanwood and WDFW | [9 empty] | Stillaguamish Watershed | 2017 | 01/14 | Waiting to sign contract with City. One councilmember would like there to be more of a visioning process before our contract starts, so prob late fall. City will let us know in fall.
SN3082 | Stanwood Trail Corridor | Michelle, Liz, Susan | 2 miles | Rural | Facilitate purchase/railbanking for Stanwood | [9 empty] | Stillaguamish Watershed | 2017 | 01/14 | City approved contract, will have June 1st effective date. Kickoff meeting with City on June 8th. On hold as TCF has asked City to wait a bit.
SN3080 | Warm Beach Property Donation | Susan | n/a | Rural | Donate to Tulalip Tribe | [9 empty] | Stillaguamish Watershed | Q1 2016 | 1/22 | Sent Tribes agreement to review.
PC3119 | Carbon River Canyon | Jordan, Charlie, Darcey | 300-500 | Rural | Facilitate purchase for Pierce County | [9 empty] | Three Rivers | 2016 | 1/22 | JR working on agreement with County & HNRG on in/operable areas and updated purchase price; DR appraisal came back at $97k value, which is enough for match from TDR funds; upon agreement, we will order the survey; we have signed a services agreement/pledge for 4%/NDA with HNRG; JR working to get funds extended into 2016
PC3115 | Franz Farm (aka Schemerhorn Farm) | Jordan, Darcey | 108 | Resource | Facilitate purchase and CE | [9 empty] | none | 2017 | - | Currently inactive, may revive at later date
PC3123 | Jacobs Point Phase II | Jordan, Darcey | 17.6 | Rural | Facilitate sale to Anderson Island Parks & Rec District | [9 empty] | Puget Sound shoreline | Q2 2016 | 1/22 | RCO grant agreement signed & project is active for ALEA funds. Jacobs family will not do an LLC, so proceeding with 3 separate ownerships. AIP&RD signed MOA, waiting to receive. Waitin gon Pierce County to send draft CFT agreement.
PC3099 | Bell Marsh | Jordan, Darcey | 21.4 | Rural | Facilitate sale to City of DuPont | [9 empty] | none | 2017 | - | Currently inactive, may revive at later date
PC3128 | White Farm | Jordan, Darcey | 143.68 | Resource | Facilitate sale to Pierce County | [9 empty] | Three Rivers | Q4 2016 | 1/22 | JR working with Pierce County on CE terms
PC3051 | Dead Man's Pond Phase II | Jordan, Darcey | 5 | Rural | Sell property to City of Puyallup | [9 empty] | Three Rivers | Q3 2017 | 1/22 | CFT app submitted, CAB ranked 14th. Opportunity fund should have $250k for 2016, CFT is funded - still awaiting further discussions RE: opportunity fund
PC3130 | Soler Family Tree Farm | Jordan, Darcey | 64 | Resource | Accept donation of fee | [9 empty] | Three Rivers | Q1 | 1/22 | ESA completed; DG reviewing cell tower lease
KG3132 | Mid Fork - Zorro Ridge | Charlie, Susan and Michelle | 20 | Rural | Facilitate purchase for DNR | [9 empty] | Snoqualmie | Q1 2016 | 1/22 | Waived contingencies, closing 1-29-16
KG3131 | Cugini - Hancock Creek (Mid Fork) | Charlie, Susan | 320 | Rural | Facilitating purchase for DNR, USFS and others | [9 empty] | Snoqualmie | 2018 | 1/22 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. Prepping to apply for Section 6 funds to acquire in 2016 round.
KG3134 | Cugini - Blethen Lake (Mid Fork) | Charlie, Susan | 240 | Rural | Facilitating purchase for DNR, USFS and others | [9 empty] | Snoqualmie | Q3 2016 | 1/22 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. Negotiating PSA with landowners. $105,000 success fee min. Plus staff time- $50,000 ish, removed.Working through apppraisal issues with Seller.
KG3135 | Cugini - Titicaed Creek | Charlie, Susan | 160 | Rural | Faciliate purchase or own in fee | [9 empty] | Tolt River | Q1- Q3 2016 | 1/22 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. Drafting Option with landowners. SPU sent LOI to take title to property. $116,000 min, minus staff time ($25,000). Working through appraisal issues with Seller.
KG3131 | Cugini - Baring | Charlie, Susan | 26 | Rural | Facilitate transaction to King County | [9 empty] | Great Northern Corridor? | Q2 2017 | 1/22 | King County management asked us to quit pushing this property for now. May apply for SRFB funds and use KC as match instead.
KG3133 | Wayne Riverfront Conservation Area- Back 9 | Michelle, Jordan, Liz, Adam, Darcey | 39 | Urban | Purchase and hold Back 9 for City of Bothell | [9 empty] | Cities for All | Q1 | 01/14 | Forterra signed acceptance of Assignment of REPSA on 06/01. Amended due diligence date from Aug 6th to Sept. No agreement on appraisal yet. Signed amendment on 11/20 to extend to 02/01/2016 closing, with $250,000 cash on 01/11. Close 02/10.
KG3133 | Wayne Riverfront Conservation Area- Front 9 | Michelle, Jordan, Liz, Adam, Darcey | 45 | Urban | Purchase and hold Front 9 for City of Bothell | [9 empty] | Cities for All | Q1 | 01/14 | Signed PSA, in due diligence period.
KG3137 | S. Fork RM 16 | Michelle, Charlie, Susan | 50 | Rural | Facilitate Transaction to DNR | [9 empty] | Snoqualmie | 2016 | 1/22 | Pledge signed, AD reviewing a contingent PSA to assign to DNR.
ES3000 | Estuary Transfers: Stafford Creek; Three Creeks | Darcey | n/a | Rural | Transfer to WDFW | [9 empty] | none | Q4/2016 | 1/22 | JR sent email to Bob Cannon on 12/22 regarding these transfers
ES3000 | Estuary Transfers: Lynn Point/South Nemah Uplands | Darcey | n/a | Rural | Transfer to Willapa National Wildlife Refuge/USFWS | [9 empty] | none | Q4 | 1/22 | Still waiting on transfer documents from USFWS. No revenue.
MN3012 | Little Skookum Inlet | Jordan, Darcey | 816 | Resource | Facilitate CE purchase for Squaxin Tribe | [9 empty] | none | 2017 | 1/22 | Gearing up for ESRP and SRFB apps
ES3063 | Wishkah Gardens | Jordan, Darcey | 72 | Rural | Facilitate purchase for CRBLT, Forterra temp hold (3 yrs) | [9 empty] | none | Q2 2016 | 1/22 | WRFB grant agreement forthcoming; need Devo's help; Jordan working on outreach to Quinault Tribe, Ducks Unlimited; DH waiting to hear from Trout Unlimited
MB6002 | Coweeman Mitigation Bank | Kurt/Hayes/Darcey | 322 | Rural | Mitigation Bank | [9 empty] | none | Q4 | 1/22 | AD sent easement drafts to Victor. Waiting.
SP3036 | Great Northern Corridor- River Access | Charlie, Darcey | n/a | n/a | [10 empty] | Great Northern Corridor | n/a | 1/22 | CPG grant app for river access on hold - the Town does not actually own this property. Thinking about RCO funding next year for acquisition. CPG to follow for river access design, and construction later.
SP3036 | Great Northern Corridor- Maloney Ridge Trails Complex | Charlie, Darcey | n/a | n/a | [10 empty] | Great Northern Corridor | n/a | 1/22 | CPG app drafted - need James to fill in general Forterra info
KS3028 | Keechelus 6 (King) | Charlie, Susan | 80 | Rural | Fee simple purchase of property | [9 empty] | I-90 Wildlife Corridor | 2016 | 1/22 | SL and CR met with landowner to try to get him to sell to Forterra and not clear cut the property with Ericcson. Sent him pledge ans Option early in October. SL in contact with landowner.
KS3080 | Starwater | Charlie, Susan | 20 | Rural | intermediary purchase, sell some to Forterra and sell off developable lots | [9 empty] | I-90 Wildlife Corridor | Q4 2016 | 1/22 | Made offer to trustee of the property for $285,000, got informal acceptance at this value and a Q1 2016 closing. Floyd providing some money to help get project started. Thuja would take title temporarily and sell to Forterra via S6. AD reviewing Thuja, CASR PSA to get property under contract ASAP.
KS3003 | Huckleberry Road/Gold Creek ReSale* | Adam, Susan | n/a | Rural | Fee simple sale | [9 empty] | I-90 Wildlife Corridor | 2015/2016 | 1/22 | Back on market with agent for $129,000, Ski Tur Valley landowners fell through. We're going for the water mitigation certificate from Suncadia contingent on Ecology approval.
KS3077 | Upper Naneum Creek | Jill, Susan | 150 | Resource | [10 empty] | Yakima River Corridor? |  |  | On hold
KS3070 | Lower Teanaway River | Jill, Susan | 100 | Rural | Facilitate for WDFW | [9 empty] | Yakima River Corridor? |  |  | On hold- Bugni.
TX9047 | Teanaway Solar Reserve | Michelle, Jill | 982 | Rural | Facilitate purchase | [9 empty] | Yakima River Corridor | 2016 | 09/23 | Susan and Liz assisting with title questions re: access. Landowner is having attorneys argue for legal access with different use, new appraisal.
TX9018 | KFBP- Port Gamble Forest- Phase 1 | Michelle, Liz | 1250 | Resource | Facilitate purchase for County | Q4 | [8 empty] | KFBP | Q2 | 01/14 | Deal off for 2015- need to determine if we are getting a PSA amendment signed or letting it lapse (Dec 16th). Discussing alternative with Ecology on Dec 15th to purchase DRs and land for 1250 acres, leave Pope with timber.
TX9018 | KFBP- Port Gamble Forest - Ride Park- Phase 3 | Michelle, Liz | 180 | Rural | Facilitate purchase for County | Q4 | [8 empty] | KFBP | 2016 | 01/14 | Ride Park funded in leg budget, need match funds. Appraisal complete, need to adjust geography. Campaign to provide match funds.
TX9018 | KFBP- Port Gamble Forest- Phase 2 | Michelle, Liz | 500 | Resource | Facilitate purchase for PGST | Q4 | [8 empty] | KFBP | Q3/Q4 2016 | 01/14 | CONFIDENTIAL- In discussion with PGST about timeline. Strategy/negotations for spending Navy funds depends on value of appraisal on Phase #1.
TX9018 | KFBP- Port Gamble Forest- remainder | Michelle, Liz | 2260 | Resource | Faciliate purchase of DRs for County | [9 empty] | KFBP | 2017 | 01/14 | TBD- funds dependent on campaign success
TX9018/TX9043 | KFBP- Hansville Block | Michelle, Liz | 1778 | Resource | Facilitate purchase for Port Gamble S'Klallam Tribe | [9 empty] | KFBP | 2016/2017 | 01/14 | On hold until Pope Resources and Tribe complete their confidential negotiations.
TX9049 | El Centro de la Raza- Phase One | Michelle | 2 | Urban | Facilitate due diligence and potential acquisition for El Centro | [9 empty] | Cities for All | 2016 | 10/29 | Forterra has partnered with El Centro to complete due diligence and potentially purchase two properties for future affordable housing/TOD. 1) Soltero Property in Beacon Hill (Seattle), 2) Rainbow Haven in Tukwila. PSA drafted for Rainbow Haven.
TX9036 | Chambers Creek | Jordan | 72 | Urban | Participate in restoration of site to enhance habitat value | [10 empty] | Q4 | 06/03 | Working with landowner and stakeholders to create site concept that incorporates restoration into development proposal. SRFB app submitted for 2015. Coordinating with stakeholders.
|  | TOTAL | 10042.28
Closed
|  | TOTAL | 0
Preliminary Projects- move up to active once you have a project code
KG3136 | South Covington Park | Liz | 3.4 | Urban | Temporary hold for City, fee simple | [9 empty] | none | unknown | 09/23 | On hold- Received PMT approval for initial project on 06/11. City received state funding for larger parcel, but may need funds to complete project vision. Discussed possible deal structure with City. Waiting to hear back.
| Weyerhauser- Lake Serene, Maloney Ridge | Charlie | [13 empty] | 2017 |  | Focus on prelim in 2016
| Dodge Ranch | Jill | 150 |  | Donate CE | [12 empty] | Focus on prelim in 2016
| Minor Ranch | Jill | 350 | [14 empty] | Focus on prelim in 2016. Apply for WWRP next year. Can we temp hold?
| Fry Creek | Jordan | [15 empty] | Focus on prelim in 2016
| Page Canyon Ranch | Jill | [15 empty] | Focus on prelim in 2016
| Western Pacific Timber land holdings | Jill | [15 empty] | Need to figure out a long term plan.
| Titicaid 2 | Charlie | [15 empty] | Focus on prelim in 2016
| Williamson Creek | Charlie | [15 empty] | Focus on prelim in 2016
| Hoquiam Surge Plain - Phase II | Jordan | 60 | Rural | Lead acquisition of property from GDRC and x-fer to Chehalis Basin Trust | [12 empty] | Discussed project with GDRC and Chehalis Basin Trust. Additional feasibility analysis needed prior to securing pledge from GDRC, applying for grant funds.
| South Prairie Creek - Partin | Jordan, Darcey | 20 | Rural | Facilitate purchase for County/Tribe | [10 empty] | TBD |  | Partnership with Pierce Conservation District, Surface Water Management and Tribe to conserve property along South Prairie Creek. In pipeline stage.
| South Prairie Creek - Decker | Jordan, Darcey | 18 | Rural | Facilitate purchase for County/Tribe | [11 empty] | 1/8 | Partnership with Pierce Conservation District, Surface Water Management and Tribe; landowner doing their own appraisal early 2015
| Yareton TDR | Jordan
| Hood Canal Salmon Enhancement Group- Property Purchase | Jordan | 30 | Rural | Transfer of property from Salmon Center to Forterra; rent back to Center | [10 empty] | Q1, 2015 |  | Follow-up needed with HCSEG ED; renting of property from Forterra deamed allowable by RCO. Need to determine whether it's feasible for Forterra to take on property.
| Hansen Ranch | Jordan | 816 | Resource | Facilitate purchase of CE to be held by County | [10 empty] | Q4 2016 |  | Toured property on August 22nd with landowner, who has expressed interest in selling CE. Follow-up to occur in September.
| Morey Creek | Jordan | 8 | Urban | Facilitate acquisition for JBLM/County | [10 empty] | Q1, 2017 |  | Discussed potential project with local stakeholders; feasibility analysis to occur in Q4, 2014.
| Swiftwater Corridor | Jill
KS6049 | Masterson Ranch | Jill
KS3073 | Greene Ranch* | Jill | 280 | Resource | Co-hold CE with KS county
| Pine Hills Ranch | Jill
| Jones Creek Canyon Ranch | Jill | [15 empty] | Priorities in the canyon
| Acheson Ranch | Jill | [15 empty] | Priorities in the canyon
| Zirkle Fruit Company | Jill | [15 empty] | Priorities in the canyon
| Edwards Ranch | Jill | [15 empty] | Priorities in the canyon
| Bristol Flats | Jill | [15 empty] | Priorities in the canyon
| Highway to Hill Farm | Jill | [15 empty] | Priorities in the canyon
| Rose Hill Farm | Jill
Discontinued Projects
PC3121 | Kannon Forest | Jordan, Darcey | 106 | Resource | CE donation | [9 empty] | none |  | 12/4 | Took too long to get Priory a CE draft. Project dead
YK3101 | Cowiche Creek | Jill, Susan | 10 | Rural | Facilitate purchase, temp hold | [9 empty] | Yakima River Corridor? |  | 1/6 | Landowner rejected offer.
GH4002 | Elk River | Michelle, Jordan, Darcey | 1742 | Rural | Facilitate purchase for State; possibly take ownership | [9 empty] | none | 2018 | - | Project inactive - landowner chose a different conservation group to pursue the project
KS3028 | Gold Creek 3 (Menconi) | Charlie, Susan | 8 | Rural | Fee simple purchase of property | [9 empty] | I-90 Wildlife Corridor |  | 1/6 | Appraisal too low, landowners rejected offer
TX9018 | KFBP- West Divide | Michelle, Liz | 484 | Resource | Facilitate purchase for County | Q4 | [8 empty] | KFBP | 2017+ | 12/03 | Kitsap County was ranked #1 DNR Community Forest Trust grant in 2014 for $3.4 M. Did not get awarded funding. Pope Resources is going to harvest some timber.
| West Rocky Prairie | Jordan | 735 | Rural | Facilitate sale for Port of Tacoma to State WDFW | [9 empty] | none |  | 08/31 | WDFW received top-ranked WWRP proposal for project. Outreach underway with Thurston Co and Port stakeholders.
LW3001 | Mineral Lake | Jordan, Charlie | 2100 | Resource | Facilitate purchase of fee for DNR | [9 empty] | none | Q1, 2016 | 08/31 | On hold- CFT application turned in to DNR in July; being vetted internally now. Rep. Orcutt has indicated that he would be willing to work with Forterra, NLT, Lewis Co and other stakeholders to prepare for 2015 session.
| Crescent Valley | Jordan
| Sperry Dock | Jordan
PC3124 | South Prairie Creek VI- Warner | Jordan, Darcey | 3.7 | Rural | Donation to Forterra; temp hold for Puyallup Tribe | [9 empty] | Puyallup/Carbon | Q3 | 8/28 | Land was purchased by Decker family. Future of this parcel unknown. Jordan still planning to have overarching conversation with Puyallup Tribe.
PC3129 | Knutson Farm | Jordan, Darcey | 175 | Resource | Facilitate sale to Pierce County | [9 empty] | Puyallup/Carbon | 2016 | - | no CFT app submitted, landowner pulled at last minute.
| Brain Ranch* | Jill | 350 | Resource | [10 empty] | Yakima River Corridor? |  | 08/31 | On hold- Jill met with Yakama Nation and Central Washington University to discuss the potential of CWU having a field station at the house on the property. Concerned appraisal will come back too low.
PC3096 | Riffe Lake Phase 2 | Jordan, Mark | 2000 | Resource | Facilitate CE purchase for TPU/WDFW | [10 empty] | TBD |  | In pipeline stage
KG3043 | Phillipa (DNR) | Susan, Charlie | [14 empty] | 08/04 | DNR working with landowner
| Olympia Brewery Project | Jordan
TX9048 | The water project | Michelle, Adam | n/a | Rural | [10 empty] | none
| Discretionary Funds WSDOT | Jill | n/a | [14 empty] | Jill still working on this?
MN3011 | Lake Nahwatzel | Jordan | 248 | Rural | Facilitate purchase for Friends of Lake Nahwatzel | Q4 | 750000 | 7% | 52500 | 10000 | 0 | 50% | 26250 | 36250 | none | 2016 | 03/25 | Working with local stakeholders, Mason Co, GDRC and Foster Pepper to establish timeline, determine costs, and complete project in next 6-9 months. Waiting for leg. decision.
SP3036/ RG240P | Foss River | Charlie, Susan | [12 empty] | none | n/a | 5/22 | KC made offer directly to WeyCo, weyco responded with a way higher counter.
KS3047 | Vickers | Jill | 30 | Rural | facilitate CE
TX9050 | Grapeview | Michelle, Liz | 15 | Rural | Fee Donation | [10 empty] | n/a | 03/24 | Asked Pastore to reimburse 14K staff/consultant expenses 01/08. Waiting to hear in Jurges (20 acre) wants to donate since we can no longer purchase. Also waiting to hear if Pastore (15 acre) wants to donate land, plus stewardship $.
| Morse Wildlife Preserve Addition | Jordan, Darcey | 25 | Rural | Purchase and add to Morse Wildlife Preserve | [11 empty] | 03/05 | Initial meeting/site visit with landowner anticipated for January/February; if landowner is willing to sell at appraised value, we will do a project code request, option, etc.
TX9037 | Bighorn Umtanum | Jill | 690 | Rural | Facilitate Purchase for WDFW | [12 empty] | Landowner declined all offers (09/03/15)
| Roesiger West | Charlie, Darcey | 206 | Resource | Facilitate purchase for DNR, possible development value with SnoCo | [11 empty] | 1/8
TX9027 | Edmonds Waterfront | Michelle, Susan | 0.03 | Urban | Facilitate purchase for City of Edmonds | Q4 | 750000 | 5% | 30000 | 0 | 0 | 50% | 15000 | 15000 |  |  |  | Landowner ignored all offers, seeing if Edmonds can change the scope if neighbors are interested in selling
SN3078 | Seabrook | Michelle, Susan |  | Urban | Facilitate for City of Lynnwood, contract. | [12 empty] | Preparing to make an offer to landowner (on behalf of City of Lynnwood)
SN3079 | Hofstra Farm | Michelle, Susan | 104 | Resource | Facilitate CE for Sno Co. | [11 empty] | 3/17 | Did not get funding from RCO
| Andrews Farm | [15 empty] | 1/8 | Landowners are not yet committed to conservation. Ok to delete, landowners could always contact us again.
| Lake Serene Trail* | Charlie
| PCT Yodelin | Charlie
| PCT Snoqualmie Pass* | Charlie
CL3050 | Pysht (Phase I) | Charlie, Darcey | 3000 | Iconic | Facilitate purchase for DNR | [12 empty] | 2015 work will include negotiations with M&R
| Stilly Buse* | Charlie | [15 empty] | TPL now
| Crystal Springs | Charlie, Susan | 4.9 |  | Facilitate purchase for WADOT | [12 empty] | DOT to communicate with landowner's agent
KG3130 | Normandy Park Nearshore | Liz | 8.72 | Urban | Facilitate purchase for City of Normandy Park | [12 empty] | Sent draft contract to new City Engineer. They are hiring a Parks Planner, so need to wait for that to happen, as well as Council approval to hire us. Maybe summer. Received Seattle Foundation commitment 03/31.
| Stossel Creek II | Charlie, Susan | 32 | Rural, Resource | Facilitate purchase for DNR | [12 empty] | Willing Landowner but not a priority to DNR
SN3077 | Arlington Farm | Michelle, Susan | 210 | Resource | Facilitate purchase of fee for Anderson family, purchase of CE for Sno County | [12 empty] | Grant Funds reallocated for Hooven Bog
TX9043 | KFBP- Hansville Block | Michelle, Liz | 1778 | Resource | Facilitate purchase for Port Gamble S'Klallam Tribe | [12 empty] | On hold indefinitely.
TX9038 | Grays Harbor Historical Seaport | Jordan | 110 | Urban | Conservation of 110 acres of flood plain habitat for County/DNR | [12 empty] | Should remove this conservation transaction as the Seaport cannot sell the property and keep revenue. Forterra to focus on RCO recreation grants to develop Seaport's new facility, paid for under Seaport contract.
SN3075 | Reiner Farm | Michelle | 300 | Rural (120), Resource (180) | Facilitate purchase for Sno County

## Contracts
Project Code | 2014 Budget | Grant/Contract ID | Project Name | Project lead | Invoicing | Role | Close Q | Purchase Price | Comp % | Success Fee | Cost Coverage | Hard Costs | Success Factor (2014) | Discount in Value | Net (not incl staff / other internal costs) | Success Factor (2015) | Important Dates | Rates | update date | Comments
Contracts/Other non transaction deals
Active
SN3074 |  | RG01FS | SRFB Lower Wallace River Grant Agreement | Susan | Susan | Purchase property, transfer to Tulalips. Forterra grant sponsor | [10 empty] | 12/31/15 expires | state determined rates | 1/6 | Final report submitted, final billing returned, final site visit next week
SN3074 |  | RG188L | Snohomish County CFT Lower Wallace River | Susan | Susan | Purchase property, transfer to Tulalips. Forterra grant sponsor | [10 empty] | 12/31/15 expires | staff time not covered, funding for purchase price and due diligence expenses | 1/6 | Final invoice submitted
SN3074 |  | RG | Lower Wallace River CE donation | Michelle | Susan | drafting CE , management plan | [12 empty] | 1/6 | Check received for full grant amount
SN3076 |  |  | Snohomish County CFT Faber Grant Agreement | Michelle, Susan, Liz | Susan | Funding for conservation easement | [11 empty] | $100,000 for conservation easement | 01/14 | Agreement signed by Forterra, waiting for County
SN3073 |  |  | Snohomish County CFT Whitehorse Mtn | Adam, Susan | Susan | Purchase property, transfer to Snohomish County. Forterra grant sponsor. | [10 empty] | Expires January 17, 2016. Renewed til when? | staff time not covered, funding for purchase price and due diligence expenses | 01/14 | Contract for up to $250,000. Effective date July 17, 2013. 30 months, so til Jan 17, 2016.
SN3082 |  | RC240L | City of Stanwood- Trail Corridor | Liz, Susan, Michelle | Susan | Facilitate acq. of Johnson Farm and Stanwood Trail Corridor | [10 empty] | Expires Dec 31, 2017 | $175 Exec, $100 Proj Mgmt, $75 Proj Assistance | 01/14 | Contract effective date June 1, 2015, monthly invoicing
SP3036 |  | RC220F | Skykomish Basin Land Protection Assessment and Mapping | Charlie, Darcey | Darcey | GIS work to map target parcels for conservation and salmon recovery | [10 empty] | Expires Dec 31, 2015 | $35.13 Tech Assoc; $65.55 Forest Consv Dir; $55.35 Geospatial Dir; $89.20 Staff Attorney | 12/11 | Forterra sub-contracted with CORE GIS for the bulk of the GIS work. Expires Dec 31, 2015. We have ~$14,000 left to bill to SnoCo this year, ~$8,000 is specifically for Forterra, remaining for CORE GIS
SP3036 |  |  | Great Northern Corridor private donations | Charlie, Darcey | Darcey | [13 empty] | 12/11 | Release from restrictions from two private donors, need to keep track of when we run out of $. Current donations sufficient through end of year; need twomajor donors to fulfill their plecge for 2016 in December
SP3036 |  | RG226P | Maloney Ridge Trails Complex - Contract with WTA for trail flagging | Charlie, Darcey | Darcey | Forterra will pay WTA for trail flagging work | [10 empty] | Expires December 31, 2015 | WTA rates of $65/hour, not to exceed $2,500 | 12/4 | COMPLETE & PAID
PC3051 |  |  | Dead Man's Pond Puyallup Agreement | Jordan, Darcey | Darcey | Buy and hold for City of Puyallup | [10 empty] | Expires June 30, 2017 | $200 staff attorney, $150 director, $115 transaction manager | 12/18 | Bill quarterly for staff time and loan interest. Property ranked low on PC CFT so Puyallup needs to figure out funding strategy or Forterra can sell it with house to anyone. City agrees to pay Forterra $336,000 plus 3% success fee at closing. Last time billed was Q3.
|  |  | Jacobs Point 2- AIPD Contract | Jordan, Darcey | Darcey | [13 empty] | 12/18 | MOA approved by PD, still need to figure out 3-parcel situation before signing
PC3125 | Y |  | Russell Family Foundation- Ag Rountable | Jordan | Darcey | Capacity funding for participation in Ag Roundtable | Q1 |  |  |  | 5000 |  | 85% | 4250 |  |  |  | $30,400 | 12/18 | Will receive funding for 2016 - total amount is $37,000 - $6,600 of which goes to Policy; meeting to discuss with Finance scheduled for 12/23
PC3126 | Y |  | Russell Family Foundation- Forest Rountable | Jordan | Darcey | Capacity funding for facilitation of Forest Roundtable | Q2 |  |  |  | 12500 |  | 65% | 8125 |  |  |  | $101,030 | 12/18 | Will receive funding for 2016; meeting to discuss with Finance scheduled for 12/23
|  |  | Puyallup Tribe Contract | Jordan | Darcey | [13 empty] | 12/18 | No contract yet. Jordan presenting to Council at end of August. Darcey will follow up with Jordan on details.
KG3121 |  |  | King County Contract | Charlie | [14 empty] | 1/6 | Adam reviewing 2016 contract.
|  |  | Kent Side Hill- Sale | Michelle | [15 empty] | See Michelle for details.
KG3131 |  | RC201P | Cugini Agreement for Professional Services | Michelle, Charlie, Susan | Susan | Facilitate property acquisition | [10 empty] | Ends Dec 31, 2016 | $200 CEO, $140 Exec, $90 Director and Staff Attorney, $75 Program Mngr, $65 Proj Mngr, $50 Admin | 1/6 | For 5 properties. Effective date January 28, 2014. Bill quarterly. Also includes 5% of monthly retainer for King County lobbyist and State Lobbyist.
KG3135, KG3134 |  |  | Mid Fork Section 6 Grant Agreement | Charlie, Susan | Susan | Facilitate property acquisition | [11 empty] | Federal rates | 1/6 | This grant is for Titicaed and Blethen. Still unsure of grant allowable reimbursements for 2015 - no contract signed with DNR
KG3133 |  | TBD | Wayne Contract with Commerce | Jordan, Liz | Darcey | Facilitate property acquisition | [10 empty] | July 1, 2015 start date | TBD | 01/14 | Received letter from Commerce with award on 08/26. Liz lead. Submitted contract readiness survey and working papers. Working through issues with Commerce.
KG3038/TR3000 |  | n/a | Seattle Foundation Donor Bequest | Liz | Liz | Faciliate purchase of park property for the Foundation | [10 empty] | no expiration date | 10% of funds, est $39,000. Exact mechanism/document TBD. | 01/14 | Sea Fdn chose two properties in Kent/Renton/Covington area, partnering with King County. $392,000 invested. Foundation okay with closing in spring 2016. Fdn will transfer $ to Forterra once PSAs signed, then Forterra transfer to County for closing.
MN3013 | N | n/a | Skokomish Tribe Contract | Jordan, Darcey | Darcey | Facilitate property transactions; develop conservation acquisition strategy | [10 empty] | Work Order #1: Conduct outreach 7/31 Secure commitments 8/30 Funding Strategy 10/15 WO end date 10/31 | No hourly rate, but use $150/hr for Director, and $115/hr for Manager. Cost per deliverable instead. | 12/18 | First Work Order complete. Waiting on Second Work Order to pursue acquisition of two properties. Contract doesn't have an expiration date, but based on agreed upon work orders.
KS3060 |  | RC227L | Kittitas County Flood Control Zone Contract (Manastash subcontract) | Jill | Susan | [13 empty] | 11/10 | will bill full contract - Susan doing title review
KS3028 |  | RG195F | I-90 Wildlife Corridor Phase V Section 6 Grant Agreement | Charlie, Susan | Susan | Subgrantee | [10 empty] | Expires Sept. 30 2016 | federal rates | 1/6 | Still have about $1M left, perhaps Starwater will eat a chunk of that.
KS3028 |  |  | I-90 Wildlife Corridor Phase VI Section 6 Grant Agreement | Charlie, Susan | Susan | Subgrantee | [10 empty] | Effective 9-15-15 Expires 9-30-17 | federal rates | 1/6 | $2,000,000 to spend!! Need Grant contract with DNR.
KS3075 |  |  | Kittitas County Brownfields | Jill | Darcey | [11 empty] | Expires Dec 31, 2015 |  | 12/18 | Darcey invoicing for Jill. About $3,750 left to bill
KS3071 |  | RC015L | Ellensburg Brownfields | Jill | Darcey | [13 empty] | 12/18 | Darcey invoicing for Jill.
KS3078 |  |  | Teanaway Contract | Jill | Darcey | Assisting with facilitating Teanway community meetings | [12 empty] | 12/18 | Darcey helping with billing.
TX9018 | Y | RC156L | Kitsap Forest and Bay Project - contract with Kitsap County | Michelle, Liz | Darcey | Facilitate purchases for County | n/a | n/a | n/a | n/a | 110000 | 54750 | n/a | n/a | 55250 |  | Expires Dec 31, 2015 | $77/hr for program staff, $125/hr for senior mgmt | 01/14 | Effective Jan 1, 2015. Contract with Kitsap County signed to pay staff expenses up to $18,000 annual, plus Konrad (3rd party) expenses up to $12,000. Bill quarterly. Liz has requested additional $ to complete the Part One acquisition this year and has asked Eric to begin amendment process.
TX9018 |  | RC221L | Kitsap Forest and Bay Project - contract with PGST | Liz | Darcey | Faciliate purchases for PGST | [10 empty] | Expires May 20, 2016 | Flat $9000 | 01/14 | Effective date May 18,2015.Contract for $9000. Can bill once in 2015 and once in 2016.
Completed
PC3120 |  |  | Frontier Park Addition Agreement with Pierce County | Jordan, Susan | Susan | Buy and hold for Pierce County | [10 empty] | Expires Dec 31, 2015 | $200 staff attorney, $150 director, $115 transaction manager | 1/6 | final payment received, contract over
Discontinued
|  |  | Mason County Trail Network | Jordan | [15 empty] | Potential project w/ Mason County to develop trail plan and apply for state funds in 2016.
|  |  | Downtown Shelton Visioning | Jordan | [15 empty] | First $18k secured; still working to secure the other $12k from City, Chamber and others.
|  |  | Puyallup River Floodplains by Design | Jordan | [15 empty] | Grant proposal submitted to Ecology 09/08. Funding anticiapted to be in the $10-$20 million range.
|  |  | City of Gig Harbor Contract | Jordan | [15 empty] | Template contracts sent to City in August; follow up to occur in September.
|  |  | City of Tumwater | Jordan | [11 empty] | 10% |  |  |  | Property tour with City to take place in September, which will help determine the scope of work for Forterra.
PC3015 |  |  | City of Tacoma | Jordan | [11 empty] | 50% |  |  |  | Exploring potential for renewed contract with the City; meeting scheduled for 09/12
PC3126 |  |  | Carbon River Forum | Jordan | [15 empty] | Next meeting on 09/23; funding for project pending, with potential sources of Pierce County and TRFF.
|  |  | Schneider Creek (Olympia) | Jordan | [11 empty] | 10% |  |  |  | Met with local stakeholders, Councilmembers, and city staff on 09/09; follow-up needed in September to secure contract.
KS3071 |  |  | 400 Mountain View Project | Jill
TX9033 | N |  | Yakima River Canyon Scenic Byway | Jill |  | running the byway initiative
TX9044 | N |  | Roslyn Urban Forest | Jill |  | grant writing, community organizing, landowner outreach etc
|  |  | Suncadia HOA | Jill

## Projects 2015
2015/16 Conservation Transactions Department Projections
Project Code | 2014 Budget | Project Name | Project lead | Acres | Land Type | Role | Close Q | Purchase Price | Comp % | Success Fee | Cost Coverage | Hard Costs | Success Factor (2014) | Discount in Value | Net (not incl staff / other internal costs) | Corridor/Focus Area | Close Q/year | Success Factor (2015) | update date | Comments | Request for Development Team
SN3073 | N | Whitehorse Mountain | Adam, Susan | 33.6 | Rural | Facilitate purchase for Sno County | [9 empty] | Stillaguamish Watershed | Q1 |  | 11/9 | Appraisal updated, came in at $290k Landowner recieved two access easements from neighbors that County requires and would raise value. PSA sent to county. | Need $25,000 or so if value of property is increased.
SN3074 | N | Lower Wallace Wetland | Michelle, Susan | 5 | Rural | Facilitate donation of easement | [9 empty] | Great Northern Corridor | Q1 2016 | n/a | 1/6 | Need to send Robinett CE, get survey of area from them
SN3076 | N | Faber Farm: Sale | Michelle, Liz, Susan | n/a | Resource | Facilitate purchase of farm on behalf of private farmer Andrew Albert. | [9 empty] | Stillaguamish Watershed | Q1 |  | 01/14 | Aiming for April closing
SN3081 |  | Johnson Farm | Michelle, Liz | 160 | Resource | Facilitate purchase of farm for Stanwood and WDFW | [9 empty] | Stillaguamish Watershed | 2017 |  | 01/14 | Waiting to sign contract with City. One councilmember would like there to be more of a visioning process before our contract starts, so prob late fall. City will let us know in fall.
SN3082 |  | Stanwood Trail Corridor | Michelle, Liz, Susan | 2 miles | Rural | Facilitate purchase/railbanking for Stanwood | [9 empty] | Stillaguamish Watershed | 2017 |  | 01/14 | City approved contract, will have June 1st effective date. Kickoff meeting with City on June 8th. On hold as TCF has asked City to wait a bit.
SN3080 |  | Warm Beach Property Donation | Susan | n/a | Rural | Donate to Tulalip Tribe | [9 empty] | Stillaguamish Watershed | Q1 2016 |  | 1/6 | Drafting agreement between Forterra and Tribes.
PC3119 | N | Carbon River Canyon | Jordan, Charlie, Darcey | 300-500 | Rural | Facilitate purchase for Pierce County | [9 empty] | Three Rivers | 2016 | 35% | 12/18 | JR working on agreement with County & HNRG on in/operable areas and updated purchase price; DR appraisal came back at $97k value, which is enough for match from TDR funds; upon agreement, we will order the survey; we have signed a services agreement/pledge for 4%/NDA with HNRG | Eleanor & Jordan working to secure additional $90k in funding; Jordan has secured $15k so far
PC3115 | N | Franz Farm (aka Schemerhorn Farm) | Jordan, Darcey | 108 | Resource | Facilitate purchase and CE | [9 empty] | none | 2017 | 40% | 12/18 | Pledge for 5% signed. CFT app submitted, CAB ranked 12th
PC3123 | N | Jacobs Point Phase II | Jordan, Darcey | 17.6 | Rural | Facilitate sale to Anderson Island Parks & Rec District | [9 empty] | Puget Sound shoreline | Q2 2016 |  | 12/18 | RCO grant agreement signed & project is active for ALEA funds. Still need Jacobs Family to decide on parcel ownership issue - Jacobs Family rep contacted Jordan this week and will be speaking to the family about the LLC idea over the holidays | Will probably need about $10k in local grant or other donation to complete acquisition. Possible option for some place-based fundraising - if CFT comes through in September, we won't need any additional funding
PC3099 |  | Bell Marsh | Jordan, Darcey | 21.4 | Rural | Facilitate sale to City of DuPont | [9 empty] | none | 2017 |  | 12/18 | CFT app submitted, pledge 7% signed. CAB ranked 13th. Gearing up for a NAWCA grant.
PC3128 |  | White Farm | Jordan, Darcey | 143.68 | Resource | Facilitate sale to Pierce County | [9 empty] | Three Rivers | Q4 2016 |  | 12/18 | Pledge for 5% signed; received CFT funding; Match: $200k FbD; may apply for EPA NEP grant
PC3051 |  | Dead Man's Pond Phase II | Jordan, Darcey | 5 | Rural | Sell property to City of Puyallup | [9 empty] | Three Rivers | Q3 2017 |  | 12/18 | CFT app submitted, CAB ranked 14th. Opportunity fund should have $250k for 2016, CFT is funded - need further discussions RE: opportunity fund
PC3130 |  | Soler Family Tree Farm | Jordan, Darcey | 64 | Resource | Accept donation of fee | [9 empty] | Three Rivers | Q4 |  | 12/18 | MOA signed; title review complete - pending review of cell tower easement/lease; cell tower lease sale (between Soler and cell co) cannot happen until January and that sale is our stewardship funding; also the ESA cannot happen until January - so for those two reasons, this donation will not occur until January
KG3132 | N | Mid Fork - Zorro Ridge | Charlie, Susan and Michelle | 20 | Rural | Facilitate purchase for DNR | [9 empty] | Snoqualmie | Q1 2016 |  | 1/6 | Almost finished fundraising, need to hear back from DNR on appraised value then waive contingencies. | Need to raise $48k to cover gap between Yellow Book Appraisal and purchase price and transaction costs/staff time.
KG3131 | N | Cugini - Hancock Creek (Mid Fork) | Charlie, Susan | 320 | Rural | Facilitating purchase for DNR, USFS and others | [9 empty] | Snoqualmie | 2018 |  | 1/6 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. DNR working to expand NRCA boundary to acquire property. Prepping to apply for Section 6 funds to acquire in 2016 round.
KG3134 | N | Cugini - Blethen Lake (Mid Fork) | Charlie, Susan | 240 | Rural | Facilitating purchase for DNR, USFS and others | [9 empty] | Snoqualmie | Q3 2016 |  | 1/6 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. Negotiating PSA with landowners. $105,000 success fee min. Plus staff time- $50,000 ish, removed.Missed appraisal window with weather, option is signed.
KG3135 |  | Cugini - Titicaed Creek | Charlie, Susan | 160 | Rural | Faciliate purchase or own in fee | [9 empty] | Tolt River | Q1- Q3 2016 |  | 1/6 | Cugini contract signed, 10% compensation minus cost coverage but cost coverage billed upfront quarterly. Drafting Option with landowners. SPU sent LOI to take title to property. $116,000 min, minus staff time ($25,000). Missed appraisal window with weather, option is signed.
KG3131 | N | Cugini - Baring | Charlie, Susan | 26 | Rural | Facilitate transaction to King County | [9 empty] | Great Northern Corridor? | Q2 2017 |  | 1/6 | King County management asked us to quit pushing this property for now
KG3133 |  | Wayne Riverfront Conservation Area- Back 9 | Michelle, Jordan, Liz, Adam, Darcey | 39 | Urban | Purchase and hold Back 9 for City of Bothell | [9 empty] | Cities for All | Q1 |  | 01/14 | Forterra signed acceptance of Assignment of REPSA on 06/01. Amended due diligence date from Aug 6th to Sept. No agreement on appraisal yet. Signed amendment on 11/20 to extend to 02/01/2016 closing, with $250,000 cash on 01/11. Close 02/10.
KG3133 |  | Wayne Riverfront Conservation Area- Front 9 | Michelle, Jordan, Liz, Adam, Darcey | 45 | Urban | Purchase and hold Front 9 for City of Bothell | [9 empty] | Cities for All | Q1 |  | 01/14 | Signed PSA, in due diligence period.
KG3137 |  | S. Fork RM 16 | Michelle, Charlie, Susan | 50 | Rural | Facilitate Transaction to DNR | [9 empty] | Snoqualmie | 2016 |  | 1/6 | Pledge signed, AD reviewing a contingent PSA to assign to DNR.
ES3000 | N | Estuary Transfers: Stafford Creek; Three Creeks | Darcey | n/a | Rural | Transfer to WDFW | [9 empty] | none | Q4/2016 |  | 12/18 | Darcey emailed Bob Cannon & Bobby Brown 8/28 and again 10/23; Mark J had meetings with Bob Cannon recently - emailed Adam, Charlie and Mark J on 10/27 for help contacting WDFW; Jordan to speak with Bob Cannon on 12/14 - will ask about these transfers!
ES3000 |  | Estuary Transfers: Lynn Point/South Nemah Uplands | Darcey | n/a | Rural | Transfer to Willapa National Wildlife Refuge/USFWS | [9 empty] | none | Q4 |  | 12/18 | Forterra pre-commercial thin complete; NRCS has approved. Waiting on transfer documents from USFWS. Aiming to close before Christmas, might not happen. No revenue.
MN3012 | N | Little Skookum Inlet | Jordan, Darcey | 816 | Resource | Facilitate CE purchase for Squaxin Tribe | [9 empty] | none | 2017 | 20% | 12/18 | Not moving forward with NCW grant app - project doesn't fit closely enough with grant parameters. Legislature did not fund WWRP high enough to receive RCO funding
ES3063 | N | Wishkah Gardens | Jordan, Darcey | 72 | Rural | Facilitate purchase for CRBLT, Forterra temp hold (3 yrs) | [9 empty] | none | Q2 2016 |  | 12/18 | SRFB awarded $101,745k. MMF, NAWCA and WFF are unlikely for match funding - need Devo's help; Jordan working on outreach to Quinault Tribe, Trout Unlimited, Ducks Unlimited; looking into Marisla Foundation | NEED HELP FINDING MATCH FUNDING. We are partnering with Chehalis Basin Land Trust on this acquisition - they will ultimately take ownership and stewardship responsibilities, but have requested our help in obtaining stewardship funding as a condition of their involvement - perhaps a good candidate for place-based fundraising?
MB6002 |  | Coweeman Mitigation Bank | Kurt/Hayes/Darcey | 322 | Rural | Mitigation Bank | [9 empty] | none | Q4 |  | 12/18 | AD sent easement drafts to Victor. Waiting.
SP3036 |  | Great Northern Corridor- River Access | Charlie, Darcey | n/a | n/a | [10 empty] | Great Northern Corridor | n/a |  | 12/18 | CPG grant app for river access on hold - the Town does not actually own this property. Thinking about RCO funding next year for acquisition. CPG to follow for river access design, and construction later. | James will assist with grant writing
SP3036 |  | Great Northern Corridor- Maloney Ridge Trails Complex | Charlie, Darcey | n/a | n/a | [10 empty] | Great Northern Corridor | n/a |  | 12/18 | CPG app drafted - need James to fill in general Forterra info; working with WTA & EMBA on grant app draft. Maloney trails contract with WTA signed - trail flagging underway | James will assist with grant writing
KS3028 |  | Keechelus 6 (King) | Charlie, Susan | 80 | Rural | Fee simple purchase of property | [9 empty] | I-90 Wildlife Corridor | 2016 |  | 1/6 | SL and CR met with landowner to try to get him to sell to Forterra and not clear cut the property with Ericcson. Sent him pledge ans Option early in October. SL left several messages | $13k in Stewardship Endowment
KS3080 |  | Starwater | Charlie, Susan | 20 | Rural | intermediary purchase, sell some to Forterra and sell off developable lots | [9 empty] | I-90 Wildlife Corridor | Q4 2016 |  | 1/6 | Made offer to trustee of the property for $285,000, got informal acceptance at this value and a Q1 2016 closing. Floyd providing some money to help get project started. Thuja would take title temporarily and sell to Forterra via S6. AD reviewing Thuja, CASR PSA to get property under contract ASAP.
KS3003 | N | Huckleberry Road/Gold Creek ReSale* | Adam, Susan | n/a | Rural | Fee simple sale | [9 empty] | I-90 Wildlife Corridor | 2015/2016 |  | 10/27 | Back on market with agent for $129,000, Ski Tur Valley landowners fell through. We're going for the water mitigation certificate from Suncadia contingent on Ecology approval.
KS3077 | N | Upper Naneum Creek | Jill, Susan | 150 | Resource | [10 empty] | Yakima River Corridor? |  |  |  | On hold
KS3070 | N | Lower Teanaway River | Jill, Susan | 100 | Rural | Facilitate for WDFW | [9 empty] | Yakima River Corridor? |  |  |  | On hold- Bugni.
TX9047 |  | Teanaway Solar Reserve | Michelle, Jill | 982 | Rural | Facilitate purchase | [9 empty] | Yakima River Corridor | 2016 |  | 09/23 | Susan and Liz assisting with title questions re: access. Landowner is having attorneys argue for legal access with different use, new appraisal.
TX9018 | Y | KFBP- Port Gamble Forest- Phase 1 | Michelle, Liz | 1250 | Resource | Facilitate purchase for County | Q4 | [8 empty] | KFBP | Q2 |  | 01/14 | Deal off for 2015- need to determine if we are getting a PSA amendment signed or letting it lapse (Dec 16th). Discussing alternative with Ecology on Dec 15th to purchase DRs and land for 1250 acres, leave Pope with timber.
TX9018 | Y | KFBP- Port Gamble Forest - Ride Park- Phase 3 | Michelle, Liz | 180 | Rural | Facilitate purchase for County | Q4 | [8 empty] | KFBP | 2016 |  | 01/14 | Ride Park funded in leg budget, need match funds. Appraisal complete, need to adjust geography. Campaign to provide match funds. | Hiring MGO
TX9018 | Y | KFBP- Port Gamble Forest- Phase 2 | Michelle, Liz | 500 | Resource | Facilitate purchase for PGST | Q4 | [8 empty] | KFBP | Q3/Q4 2016 |  | 01/14 | CONFIDENTIAL- In discussion with PGST about timeline. Strategy/negotations for spending Navy funds depends on value of appraisal on Phase #1.
TX9018 |  | KFBP- Port Gamble Forest- remainder | Michelle, Liz | 2260 | Resource | Faciliate purchase of DRs for County | [9 empty] | KFBP | 2017 |  | 01/14 | TBD- funds dependent on campaign success
TX9018/TX9043 | N | KFBP- Hansville Block | Michelle, Liz | 1778 | Resource | Facilitate purchase for Port Gamble S'Klallam Tribe | [9 empty] | KFBP | 2016/2017 |  | 01/14 | On hold until Pope Resources and Tribe complete their confidential negotiations.
TX9049 | N | El Centro de la Raza- Phase One | Michelle | 2 | Urban | Facilitate due diligence and potential acquisition for El Centro | [9 empty] | Cities for All | 2016 |  | 10/29 | Forterra has partnered with El Centro to complete due diligence and potentially purchase two properties for future affordable housing/TOD. 1) Soltero Property in Beacon Hill (Seattle), 2) Rainbow Haven in Tukwila. PSA drafted for Rainbow Haven.
TX9036 | N | Chambers Creek | Jordan | 72 | Urban | Participate in restoration of site to enhance habitat value | [10 empty] | Q4 | 25% | 06/03 | Working with landowner and stakeholders to create site concept that incorporates restoration into development proposal. SRFB app submitted for 2015. Coordinating with stakeholders.
|  |  | TOTAL | 10042.28
Closed
ES3061 |  | Sunshine Coast | Darcey | n/a | Rural | Transfer to WDFW | [9 empty] | none | Q1 |  | 1/8 | Transfer to Willapa National Wildlife Refuge completed on 1/7/15
PC3118 | Y | Matlock Farm | Jordan, Darcey | 153 | Resource | Facilitate (County holds development easement; private entity purchases farm; other agency purchases riparian) | Q4 | 3200000 | 5% | 160000 | 15000 | 0 | 55% | 88000 | 88000 | Puyallup/Carbon River | Q1 | n/a | 03/05 | Closed 02/17!
TX9018/TX9041 | N | KFBP- Grovers Creek Preserve (Divide Block) | Liz | 175 | Rural | Facilitate purchase for Great Peninsula Conservancy | Q4 | [8 empty] | none | Q2 |  | 04/30 | Closed 04/30!
KS3074 |  | Amon Creek Minerals Sale | Michelle, Adam, Susan | n/a | n/a | [11 empty] | Q3 |  | 08/04 | Closed 8/5/15
SN3074 | N | Lower Wallace River Conservation Area | Michelle, Susan | 121 | Rural | Facilitate purchase for Tulalip Tribe | [9 empty] | Great Northern Corridor | Q3 | n/a | 09/16 | Closed! Forterra acquired, transferred to Tulalip, closing out grants, received Tulalip grant money.
PC3120 |  | Frontier Park Addition- Sale | Jordan, Susan | n/a | Urban | Transfer property to County | [9 empty] | none | Q3 | 85% | 09/16 | Closed Sept 17th.
ES6019 | N | Lake Ozette/Umbrella Bay- Phase 2 | Adam, Darcey | n/a | Rural | Sell to Makah Tribe | [9 empty] | none | Q4 |  | 11/9 | Closing date Nov 20; closing docs circulating for signature; revenue will be $291,363.49 (sale price + 3% interest)
SN3076 | N | Faber Farm | Michelle, Liz, Susan | 140 | Resource | Facilitate purchase of farm on behalf of private farmer Andrew Albert. | [9 empty] | Stillaguamish Watershed | Q4 |  | 01/14 | Feds approved offer of $450,000, plus we owe $35,000 in taxes to SnoCo. Applying for Plat amendment and put up notices on the property. Signed Loan Purchase and Sale Agreement with Union Bank on 10/12. Have until Dec 4th to satisfy contigencies. Close on Dec 16th. Simultaneously close with Riverbend Investment LLC on the deed in lieu.
|  |  | TOTAL | 589
Preliminary Projects- move up to active once you have a project code
KG3136 |  | South Covington Park | Liz | 3.4 | Urban | Temporary hold for City, fee simple | [9 empty] | none | unknown |  | 09/23 | On hold- Received PMT approval for initial project on 06/11. City received state funding for larger parcel, but may need funds to complete project vision. Discussed possible deal structure with City. Waiting to hear back.
|  | Weyerhauser- Lake Serene, Maloney Ridge | Charlie | [13 empty] | 2017 |  |  | Focus on prelim in 2016
|  | Dodge Ranch | Jill | 150 |  | Donate CE | [13 empty] | Focus on prelim in 2016
|  | Minor Ranch | Jill | 350 | [15 empty] | Focus on prelim in 2016. Apply for WWRP next year. Can we temp hold?
|  | Fry Creek | Jordan | [16 empty] | Focus on prelim in 2016
|  | Page Canyon Ranch | Jill | [16 empty] | Focus on prelim in 2016
|  | Western Pacific Timber land holdings | Jill | [16 empty] | Need to figure out a long term plan.
|  | Titicaid 2 | Charlie | [16 empty] | Focus on prelim in 2016
|  | Williamson Creek | Charlie | [16 empty] | Focus on prelim in 2016
|  | Hoquiam Surge Plain - Phase II | Jordan | 60 | Rural | Lead acquisition of property from GDRC and x-fer to Chehalis Basin Trust | [11 empty] | 0% |  | Discussed project with GDRC and Chehalis Basin Trust. Additional feasibility analysis needed prior to securing pledge from GDRC, applying for grant funds.
| N | South Prairie Creek - Partin | Jordan, Darcey | 20 | Rural | Facilitate purchase for County/Tribe | [10 empty] | TBD |  |  | Partnership with Pierce Conservation District, Surface Water Management and Tribe to conserve property along South Prairie Creek. In pipeline stage.
| N | South Prairie Creek - Decker | Jordan, Darcey | 18 | Rural | Facilitate purchase for County/Tribe | [11 empty] | 0% | 1/8 | Partnership with Pierce Conservation District, Surface Water Management and Tribe; landowner doing their own appraisal early 2015
|  | Yareton TDR | Jordan
|  | Hood Canal Salmon Enhancement Group- Property Purchase | Jordan | 30 | Rural | Transfer of property from Salmon Center to Forterra; rent back to Center | [10 empty] | Q1, 2015 | 15% |  | Follow-up needed with HCSEG ED; renting of property from Forterra deamed allowable by RCO. Need to determine whether it's feasible for Forterra to take on property.
|  | Hansen Ranch | Jordan | 816 | Resource | Facilitate purchase of CE to be held by County | [10 empty] | Q4 2016 |  |  | Toured property on August 22nd with landowner, who has expressed interest in selling CE. Follow-up to occur in September.
|  | Morey Creek | Jordan | 8 | Urban | Facilitate acquisition for JBLM/County | [10 empty] | Q1, 2017 | 0% |  | Discussed potential project with local stakeholders; feasibility analysis to occur in Q4, 2014.
|  | Swiftwater Corridor | Jill
KS6049 | N | Masterson Ranch | Jill
KS3073 | N | Greene Ranch* | Jill | 280 | Resource | Co-hold CE with KS county
|  | Pine Hills Ranch | Jill
|  | Jones Creek Canyon Ranch | Jill | [16 empty] | Priorities in the canyon
|  | Acheson Ranch | Jill | [16 empty] | Priorities in the canyon
|  | Zirkle Fruit Company | Jill | [16 empty] | Priorities in the canyon
|  | Edwards Ranch | Jill | [16 empty] | Priorities in the canyon
|  | Bristol Flats | Jill | [16 empty] | Priorities in the canyon
|  | Highway to Hill Farm | Jill | [16 empty] | Priorities in the canyon
|  | Rose Hill Farm | Jill
Discontinued Projects
PC3121 |  | Kannon Forest | Jordan, Darcey | 106 | Resource | CE donation | [9 empty] | none |  |  | 12/4 | Took too long to get Priory a CE draft. Project dead
YK3101 |  | Cowiche Creek | Jill, Susan | 10 | Rural | Facilitate purchase, temp hold | [9 empty] | Yakima River Corridor? |  |  | 1/6 | Landowner rejected offer. | $100k to purchase property
GH4002 |  | Elk River | Michelle, Jordan, Darcey | 1742 | Rural | Facilitate purchase for State; possibly take ownership | [9 empty] | none | 2018 |  | - | Project inactive - landowner chose a different conservation group to pursue the project
KS3028 |  | Gold Creek 3 (Menconi) | Charlie, Susan | 8 | Rural | Fee simple purchase of property | [9 empty] | I-90 Wildlife Corridor |  |  | 1/6 | Appraisal too low, landowners rejected offer
TX9018 | N | KFBP- West Divide | Michelle, Liz | 484 | Resource | Facilitate purchase for County | Q4 | [8 empty] | KFBP | 2017+ |  | 12/03 | Kitsap County was ranked #1 DNR Community Forest Trust grant in 2014 for $3.4 M. Did not get awarded funding. Pope Resources is going to harvest some timber.
|  | West Rocky Prairie | Jordan | 735 | Rural | Facilitate sale for Port of Tacoma to State WDFW | [9 empty] | none |  | 40% | 08/31 | WDFW received top-ranked WWRP proposal for project. Outreach underway with Thurston Co and Port stakeholders.
LW3001 | N | Mineral Lake | Jordan, Charlie | 2100 | Resource | Facilitate purchase of fee for DNR | [9 empty] | none | Q1, 2016 | 25% | 08/31 | On hold- CFT application turned in to DNR in July; being vetted internally now. Rep. Orcutt has indicated that he would be willing to work with Forterra, NLT, Lewis Co and other stakeholders to prepare for 2015 session.
|  | Crescent Valley | Jordan
|  | Sperry Dock | Jordan
PC3124 |  | South Prairie Creek VI- Warner | Jordan, Darcey | 3.7 | Rural | Donation to Forterra; temp hold for Puyallup Tribe | [9 empty] | Puyallup/Carbon | Q3 |  | 8/28 | Land was purchased by Decker family. Future of this parcel unknown. Jordan still planning to have overarching conversation with Puyallup Tribe.
PC3129 |  | Knutson Farm | Jordan, Darcey | 175 | Resource | Facilitate sale to Pierce County | [9 empty] | Puyallup/Carbon | 2016 |  | - | no CFT app submitted, landowner pulled at last minute.
| N | Brain Ranch* | Jill | 350 | Resource | [10 empty] | Yakima River Corridor? |  |  | 08/31 | On hold- Jill met with Yakama Nation and Central Washington University to discuss the potential of CWU having a field station at the house on the property. Concerned appraisal will come back too low.
PC3096 | N | Riffe Lake Phase 2 | Jordan, Mark | 2000 | Resource | Facilitate CE purchase for TPU/WDFW | [10 empty] | TBD | 15% |  | In pipeline stage
KG3043 |  | Phillipa (DNR) | Susan, Charlie | [15 empty] | 08/04 | DNR working with landowner
|  | Olympia Brewery Project | Jordan
TX9048 | N | The water project | Michelle, Adam | n/a | Rural | [10 empty] | none
|  | Discretionary Funds WSDOT | Jill | n/a | [15 empty] | Jill still working on this?
MN3011 | Y | Lake Nahwatzel | Jordan | 248 | Rural | Facilitate purchase for Friends of Lake Nahwatzel | Q4 | 750000 | 7% | 52500 | 10000 | 0 | 50% | 26250 | 36250 | none | 2016 | n/a | 03/25 | Working with local stakeholders, Mason Co, GDRC and Foster Pepper to establish timeline, determine costs, and complete project in next 6-9 months. Waiting for leg. decision.
SP3036/ RG240P |  | Foss River | Charlie, Susan | [12 empty] | none | n/a |  | 5/22 | KC made offer directly to WeyCo, weyco responded with a way higher counter.
KS3047 |  | Vickers | Jill | 30 | Rural | facilitate CE
TX9050 | N | Grapeview | Michelle, Liz | 15 | Rural | Fee Donation | [10 empty] | n/a |  | 03/24 | Asked Pastore to reimburse 14K staff/consultant expenses 01/08. Waiting to hear in Jurges (20 acre) wants to donate since we can no longer purchase. Also waiting to hear if Pastore (15 acre) wants to donate land, plus stewardship $.
|  | Morse Wildlife Preserve Addition | Jordan, Darcey | 25 | Rural | Purchase and add to Morse Wildlife Preserve | [11 empty] | 0% | 03/05 | Initial meeting/site visit with landowner anticipated for January/February; if landowner is willing to sell at appraised value, we will do a project code request, option, etc. | May need some assistance finding/raising stewardship funding
TX9037 | Y | Bighorn Umtanum | Jill | 690 | Rural | Facilitate Purchase for WDFW | [13 empty] | Landowner declined all offers (09/03/15)
| N | Roesiger West | Charlie, Darcey | 206 | Resource | Facilitate purchase for DNR, possible development value with SnoCo | [12 empty] | 1/8
TX9027 | Y | Edmonds Waterfront | Michelle, Susan | 0.03 | Urban | Facilitate purchase for City of Edmonds | Q4 | 750000 | 5% | 30000 | 0 | 0 | 50% | 15000 | 15000 |  |  |  |  | Landowner ignored all offers, seeing if Edmonds can change the scope if neighbors are interested in selling
SN3078 | N | Seabrook | Michelle, Susan |  | Urban | Facilitate for City of Lynnwood, contract. | [13 empty] | Preparing to make an offer to landowner (on behalf of City of Lynnwood)
SN3079 | N | Hofstra Farm | Michelle, Susan | 104 | Resource | Facilitate CE for Sno Co. | [12 empty] | 3/17 | Did not get funding from RCO | Need $$ for Purchase of conservation easement!
| N | Andrews Farm | [16 empty] | 1/8 | Landowners are not yet committed to conservation. Ok to delete, landowners could always contact us again.
| N | Lake Serene Trail* | Charlie
| N | PCT Yodelin | Charlie
| N | PCT Snoqualmie Pass* | Charlie
CL3050 | Y | Pysht (Phase I) | Charlie, Darcey | 3000 | Iconic | Facilitate purchase for DNR | [13 empty] | 2015 work will include negotiations with M&R
| N | Stilly Buse* | Charlie | [16 empty] | TPL now
| N | Crystal Springs | Charlie, Susan | 4.9 |  | Facilitate purchase for WADOT | [13 empty] | DOT to communicate with landowner's agent
KG3130 | N | Normandy Park Nearshore | Liz | 8.72 | Urban | Facilitate purchase for City of Normandy Park | [13 empty] | Sent draft contract to new City Engineer. They are hiring a Parks Planner, so need to wait for that to happen, as well as Council approval to hire us. Maybe summer. Received Seattle Foundation commitment 03/31.
| N | Stossel Creek II | Charlie, Susan | 32 | Rural, Resource | Facilitate purchase for DNR | [13 empty] | Willing Landowner but not a priority to DNR
SN3077 | N | Arlington Farm | Michelle, Susan | 210 | Resource | Facilitate purchase of fee for Anderson family, purchase of CE for Sno County | [13 empty] | Grant Funds reallocated for Hooven Bog
TX9043 | N | KFBP- Hansville Block | Michelle, Liz | 1778 | Resource | Facilitate purchase for Port Gamble S'Klallam Tribe | [13 empty] | On hold indefinitely.
TX9038 | N | Grays Harbor Historical Seaport | Jordan | 110 | Urban | Conservation of 110 acres of flood plain habitat for County/DNR | [11 empty] | 20% |  | Should remove this conservation transaction as the Seaport cannot sell the property and keep revenue. Forterra to focus on RCO recreation grants to develop Seaport's new facility, paid for under Seaport contract.
SN3075 | N | Reiner Farm | Michelle | 300 | Rural (120), Resource (180) | Facilitate purchase for Sno County

## Budget 2016 Dept 16
Project Management Matrix
Lead Employee's Name
Project Code | Project Name | Project lead | Role | Close Q | Purchase Price | Comp % | Success Fee | Cost Coverage | Hard Costs | Success Factor (2016) | Discount in Value | Comments | Location | Program (Corridors/City) | Budgeted Total transaction Cost* | Actual lifetime transaction costs | Fiscal year transaction costs | Title Report Ordered (Date) | Title Exceptions | Appraisal Requested (Date) | Comparables Approved | Approved Appraised Value | Willing Seller Letter Received | Pledge Agreement Secured | Compensation Sources Secured for Acquisition | Compensation Sources Secured for Transaction Costs | Current Challenges | Next Steps | Last Review Date with Direct Supervisor
IN BUDGET
PC3123 | Jacobs Point Phase II | Jordan, Darcey | Facilitate sale to Anderson Island Parks & Rec District | Q2 | 115000 | 7% | 8050 | 5750 | N/A | 80% | 11040 | Conservation Futures, ALEA, and WWRP secured; closing anticipated in Q1, 2016
PC3128 | White Farm | Jordan, Darcey | Facilitate sale to Pierce County | Q4 | 1000000 | 5% | 50000 | 52500 | N/A | 50% | 51250 | Match: $650k secured from Conservation Futures as well as $200k FbD; also either NEP or CREP for remaining balance. CE value may be $1,147,000
ES3063 | Wishkah Gardens | Jordan, Darcey | Facilitate purchase for CRBLT, Forterra temp hold (3 yrs) | Q3 | 83000 | 7% | 5810 | 4700 | N/A | 60% | 6306 | SRFB funds allocated for 85% of project cost; determining matching fund(s) for remaining $17k
KG3134 | Cugini - Blethen Lake (Mid Fork) | Charlie, Susan | Facilitating purchase for DNR, USFS and others | Q1-Q3 | 1057000 | 10% less staff time | 65700 | 4000 | covered by DNR/Cugini | 60% | 41820 | Cost coverage for staff time from Cugini Contract ($2000) and Section 6 contract ($2000). More complicated transaction than Titicaed.
KG3135 | Cugini - Titicaed Creek | Charlie, Susan | Faciliate purchase or own in fee | Q1- Q3 | 1167000 | 10% less staff time | 93200 | 3500 | covered by DNR/Cugini | 60% | 58020 | $1,500 Cugini and $2k S6
IN PIPELINE | [10 empty] | 168436
PC3051 | Dead Man's Pond Phase II | Jordan, Darcey | Sell property to City of Puyallup | Q3 2017 | 336000 | 3% | 10080 | 15000 | N/A | 20% | 5016 | Opportunity fund should have $250k for 2016, need CFT to be funded before having further discussions
PC3119 | Carbon River Canyon | Jordan, Darcey | Facilitate purchase for Pierce County | Q1 | 900000 | 3% | 27000 | See contract below | N/A | 40% | 10800 | Too uncertain for PowerPlan. Cost coverage from CFT.
KS3028 | Keechelus 6 (King) | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | Q3 | 330000 | 7% | 10100 | See contract below | covered by DNR | 45% | 4545 | Stewardship is subtracted from the 7% success fee. Cost coverage estimate $3000, see contract below.
KS3080 | Starwater | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | Q2 | 400000 | 5% | 20000 | See contract below | covered by DNR | 45% | 9000 | Intermediary purchase, sell some to Forterra and sell off developable lots; need grant amendment. Cost coverage estimate $3000, see contract below.
| Zirkle Fruit Company | Jill | CE Donation | Q4 | 1000000 | 5% | 50000 |  |  | 35% | 17500 | Need to establish relationship with Zirkle and seek donation
| Highway to Hill Farm | Jill | CE Donation | Q4 | 1000000 | 5% | 50000 |  |  | 25% | 12500 | Need to build on relationship with landowners and discuss terms
| Dodge Farm | Jill | CE Donation | Q4 | 450000 | 3% | 13500 |  |  | 51% | 6885 | Need to build on relationship with landowners and discuss terms
66246
Contracts
Project Code | Project Name | Project lead | Role | Amount |  | Rates |  | Important Dates |  | Success Factor (2016) | Discount in Value | Comments
IN BUDGET
SP3036 | Great Northern Corridor private donations; RG226P, RG240P | Darcey, Charlie | Develop recreation projects and conservation transactions in Upper Sky | 70000 |  | External |  | Through 12-31-2016 |  | 80% | 56000 | Half to staff time, half to overhead
TBD | Puyallup Tribe Contract | Jordan | Facilitate acquisitions as determined by Council; likely targets: Lake Kapowsin and Diru Creek | 12000 |  | $150/hr for Director, and $115/hr for Manager |  | TBD |  | 65% | 7800 | List of target properties being refined now; Council direction to be provided in October/November 2015
MN3013 | Skokomish Tribe Contract | Jordan, Darcey | Facilitate acquisitions as determined by Tribe; partner on grant applications as needed | 15000 |  | No hourly rate, but use $150/hr for Director, and $115/hr for Manager. Cost per deliverable instead. |  |  |  | 80% | 12000 | Forterra is under contract, but work order(s) for 2015 have yet to be fleshed out based on first work order. Certainty will go up in November, 2016
KG3133 | Wayne Contract with Commerce | Michelle, Jordan, Liz | Facilitate property acquisition, community stakeholder discussion, and property disposition | 100000 |  | TBD- $200 staff attorney, $150 director, $115 manager? |  | TBD- April 2015 start date, Dec 2018 end date? |  | 50% | 50000 | The amount of funds we recover for staff time, hard costs, etc. is dependent on one or both of the transactions moving forward. Need to adust amount and work with Melissa further.
KG3121 | King County Contract | Charlie | Work on recreation and conservation in Skykomish valley | 20000 |  | External |  | Through 12-31-2016 |  | 80% | 16000 | Need County Council approval; additional $20,000 to Policy
KG3131/RC201P | Cugini Agreement for Professional Services | Michelle, Charlie, Susan | Building up Hancock Creek, Baring and Hogarty to project status | 7500 |  | $200 CEO, $140 Exec, $90 Director and Staff Attorney, $75 Program Mngr, $65 Proj Mngr, $50 Admin |  | Expires 12/31/2016 |  | 75% | 5625 | Titicaed and Blethen reflected in transaction
KG3132, KG3134 | Mid Fork Section 6 Grant Agreement | Charlie, Susan | Hancock Creek staff time | 1000 |  | Federal |  | probably starts Sept. 2016 |  | 51% | 510 | Blethen and Titicaed reflected in transaction. This is included under Cugini general project code, under federal revenue.
KS3028/RG195F | I-90 Wildlife Corridor Phase V Section 6 Grant Agreement | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | 6000 |  | Federal |  |  |  | 60% | 3600 | See Keechelus 6 and Starwater cost coverage. Expect $3000 from each project. Will bill to Phase VI grant agreement when funds are used up in Phase V.
IN PIPELINE | [10 empty] | 151535
SN3082 | City of Stanwood- Trail Corridor | Liz, Susan, Michelle | Facilitate acq. of Stanwood Trail Corridor |  |  | $175 Exec, $100 Proj Mgmt, $75 Proj Assistance |  | Expires Dec 31, 2017 |  |  |  | Currently on hold- not entering in budget this year.
PC3051 | Dead Man's Pond Puyallup Agreement | Jordan, Darcey | Sell property to City of Puyallup | [8 empty] | Info included in project budget above.
PC3123 | Jacobs Point 2- AIPD Contract | Jordan, Darcey | Facilitate sale to Anderson Island Parks & Rec District | [8 empty] | Info included in project budget above.
PC3119 | Carbon River Canyon | Jordan, Darcey | Facilitate purchase for Pierce County | 42000 | [5 empty] | 40% | 16800 | Cost coverage from CFT.
KG3038/TR3000 | Seattle Foundation Donor Bequest | Liz | Faciliate purchase of park property for the Foundation | 39000 |  | 10% of funds, est $39,000. Exact mechanism/document TBD. |  | no expiration date, prefer funds spent in 2015 |  | 40% | 15600 | Sea Fdn chose two properties in Kent/Renton/Covington area, partnering with King County. $392,000 invested. Foundation prefer closing to happen by end of 2015. Fdn will transfer $ to Forterra once PSAs signed, then Forterra transfer to County for closing.
KS3028/RG275F | I-90 Wildlife Corridor Phase VI Section 6 Grant Agreement | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | n/a |  | Federal |  |  |  | n/a |  | Will bill to Phase VI grant agreement when funds are used up in Phase V. Will use in 2017.
TX9023 | Yakima River Canyon Scenic Byway - Major Donor/Place Based Fundraising | Jill | Leading effort | 100000 |  | External |  | n/a |  | 40% | 40000 | need to have Gene continue to pursue major donors and Eleanor/crew to help with place based campaign. Conservation Fund grant in here too
TX9023 | Yakima River Canyon Scenic Byway - Legislative Ask and Contract with??? | Jill | 2016 ask for $500k into legislature with a request for contract to 'do the work' with WSDOT?/County??? | 100000 |  | External |  |  |  | 25% | 25000 | most of the funding would go to WSDOT, but I'm setting up ask to see if Forterra could get a contract out of it for general canyon work
YK3010 | Cowiche Canyon | Jill | possible contract with City or County to help facilitate trail and stakeholder groups, acquiring property etc | 25000 |  | External |  |  |  | 5% | 1250 | Jill working to see if there is a role for Forterra to help with Corridor planning there - or alternately a contract with City for assistance with spending federal $$
TX9023 | Eaton Ranch | Gene/Jill | Lead negotiator, project lead | 100000 |  | External |  |  |  | 25% | 25000 | attempt to purchase the Eaton Ranch (or CE purchase) with YBIP funding - maybe a contract with WDFW/YBIP/County?
tbd | Farmland Conservation Program Development | Jill | seeking major donors to support farmland conservation in Yakima Basin - also possible contract with County if I can convince them | 100000 |  | External |  |  |  | 5% | 5000 | Jill will need help with creating a farmland program to attract major donors to support our work and payments to farmers to hold land open while waiting for conservation grant $$
| Swiftwater Corridor | Jill | developing program for Corridor - contract with WSDOT? | 25000 |  | External |  |  |  | 10% | 2500 | roll this into legislative ask?
KS3060 | Kit Co Flood Control Zone District - Acquisition Contract/Maybe Bugni | Jill | possible contract for continuing work on floodplain acquisitions and grant writing for the County | 25000 |  | External |  |  |  | 15% | 3750 | Won't know about more contract work until end of the year or early 2016
[11 empty] | 134900 |  |  |  | *summary budget as note - hard costs, employee costs.
Note on K18: Liz Johnston: Too high for such uncertainty, don't include in budget

## Budget 2016 Dept 90 MC
2016 Projections for EVPSE Projects
**Note, Dept 16 code projects are included in 3rd tab.
Project Code | Project Name | Project lead | Role | Close Q | Purchase Price | Comp % | Success Fee | Cost Coverage | Hard Costs | Success Factor (2016) | Discount in Value | Comments
KG3134 | Cugini - Blethen Lake (Mid Fork) | Charlie, Susan | Facilitating purchase for DNR, USFS and others | Q1-Q3 2016 | 1057000 | 10% less staff time | 65700 | 4000 | covered by DNR/Cugini | 60% | 41820 | Cost coverage for staff time from Cugini Contract ($2000) and Section 6 contract ($2000).
KG3135 | Cugini - Titicaed Creek | Charlie, Susan | Faciliate purchase or own in fee | Q1- Q3 2016 | 1167000 | 10% less staff time | 93200 | 3500 | covered by DNR/Cugini | 70% | 67690 | $1,500 Cugini and $2k S6
KS3028 | Keechelus 6 | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | Q3 2016 | 330000 | 7% | 10100 | 3000 | covered by DNR | 51% | 6681 | Stewardship is subtracted from the 7% success fee
KS3080 | Starwater | Charlie, Susan | Facilitate purchase with I-90 Section 6 Funds | Q2 2016 | 400000 | 5% | 20000 | 3000 | covered by DNR | 51% | 11730 | Intermediary purchase, sell some to Forterra and sell off developable lots; need grant amendment
TX9018 | KFBP- Port Gamble Forest- Phase 2 | Michelle, Liz | Facilitate purchase for PGST | Q4 2016 | 1000000 | 6.5% | 65000 | All covered through contract | n/a | 35% | 22750 | Port Gamble Forest Phase 2 sale could be $1,000,000 to $3,000,000. Due to uncertainty, included $1 mil.
TX90247 | Cle Elum Ridge - Specifically Masterson, Pine Hills Ranch and Solar Farm | Michelle and Jill | Michelle needs to complete this section -
TX9047 | Teanaway Solar Reserve | Michelle
SN3076 | Faber Farm | Michelle, Susan | Facilitate purchase of farm on behalf of private farmer Andrew Albert.
150671
Contracts
Project Code | Project Name | Project lead | Role | Amount |  | Rates |  | Important Dates |  | Success Factor (2016) | Discount in Value | Comments
SN3082 | City of Stanwood- Trail Corridor | Liz, Susan, Michelle | Facilitate acq. of Stanwood Trail Corridor |  |  | $175 Exec, $100 Proj Mgmt, $75 Proj Assistance |  | Expires Dec 31, 2017 |  |  |  | Currently on hold
KG3131/RC201P | Cugini Agreement for Professional Services | Michelle, Charlie, Susan | Building up Hancock Creek, Baring and Hogarty to project status | 10000 |  | $200 CEO, $140 Exec, $90 Director and Staff Attorney, $75 Program Mngr, $65 Proj Mngr, $50 Admin |  | Expires 12/31/2016 |  | 80% | 8000 | Titicaed and Blethen reflected in transaction
KG3132, KG3134 | Mid Fork Section 6 Grant Agreement | Charlie, Susan | Hancock Creek staff time | 1000 |  | Federal |  | probably starts Sept. 2016 |  | 51% | 510 | Blethen and Titicaed reflected in transaction
KG3133 | Wayne Contract with Commerce | Jordan, Liz | Facilitate property acquisition, community stakeholder discussion, and property disposition | 100000 |  | TBD- $200 staff attorney, $150 director, $115 manager? |  | TBD- April 2015 start date, Dec 2018 end date? |  | 30% | 30000 | The amount of funds we recover for staff time, hard costs, etc. is dependent on one or both of the transactions moving forward. Need to adust amount and work with Melissa further.
TX9018/RC156L | Kitsap Forest and Bay Project - contract with Kitsap County | Michelle, Liz | Facilitate purchases for County | 20000 |  | $77/hr for program staff, $125/hr for senior mgmt |  | Jan-Dec 2016 |  | 50% | 10000
TX9018/RC221L | Kitsap Forest and Bay Project - contract with PGST | Liz | Faciliate purchases for PGST | 5000 |  | Flat rate |  | Expires May 20, 2016 |  | 50% | 2500
TX9052 | Kitsap Forest and Bay Project- Port Gamble Heritage Park Community Campaign | Michelle, Eleanor, Liz | Lead and coordinate campaign to purchase property in Port Gamble Forest Block | 50000 |  | 10% of amount raised/spent on transaction |  | no specific dates |  |  |  | We can take 10% of what we raise from the campaign, however will be balancing the amount based on actual expenses, success fee from landowner, and other factors yet tbd.